## ResourceEffort64v14-1
SNo | Project | Primary Tasks | Secondary Task | Resource | Role | W1 Hrs | W2 Hrs | W3 Hrs | W4 Hrs(Projected) | W5 Hrs (Projected) | Combined Hours | Total Hrs | Comment
1 | Quincy Devp. Projects | Documentation |  | Rajan Singh | .Net Developer | 14 | 0 |  | 10 | 15 | 69 | 118
|  | Development API |  |  |  | 0 | 30 |  | 0 | 0
| SIR Dev & documentation | SIR - EDocs |  |  |  | 10 | 0 |  | 30 | 9 | 49
2 | Python Raters Rewrite PAP | UAT Testing Support PAP |  | Praveen Kumar | QA Tester | 16 | 8 |  | 8 | 8 | 120 | 120 | Hours are for UAT support i.e defects replication, Internal dev co-ordination, re-testing & recreation of defects. From W3 the hours are projected hours only if any defect reported from client end. (Total estimated hours - 54) Hours are for UAT testing for all 03 state included Client provided scenarios (Total Estimated hours 164) - (Hours for April month 122) = 42 hours remaining (till 2nd week of May) i.e expected completion timeline. *Note for April -W5 we have only 04 working days
| Quincy PAP Automation Enhancement | PAP Manual Data Creation, Execution & Validation |  |  |  | 0 | 32 |  | 32 | 16
3 | WINS Documentation | DFA Screen Field Mapping |  | Ankita Naskar | COBOL Developer | 12 | 16 |  | 2 | 0 | 60 | 60
|  | Field Mapping of BOP/HOP |  |  |  | 0 | 0 |  | 18 | 12
4 | RPA Report Support | RPA Monthly Reports Execution & Validation |  | Raginee Singh | RPA Developer | 0 | 6 |  | 8 | 0 | 104 | 104
| Quincy PAP Automation Enhancement | New Screen-Policy Information |  |  |  | 0 | 34 |  | 32 | 24
5 | WINS Documentation | DFA Screen Field Mapping |  | Jyotirmoy Adhikary | COBOL Developer | 12 | 16 |  | 2 | 0 | 60 | 60
|  | Field Mapping of BOP/HOP |  |  |  | 0 | 0 |  | 18 | 12
6 | Python Raters Rewrite PAP | UAT Testing Support PAP |  | Maanik Kapoor | COBOL Developer | 12 | 8 |  | 20 | 12 | 52 | 136
|  | Regression Defect Fixing |  |  |  | 6 | 0 |  | 10 | 10 | 26
| WINS Documentation | DFA and additional lines |  |  |  | 6 | 0 |  | 10 | 10 | 26
|  | DFA Endorsement |  |  |  | 0 | 32 |  | 0 | 0 | 32
7 | WINS Documentation | Documentation and review |  | Shayak Ghosh | COBOL Developer | 24 | 0 |  | 40 | 24 | 88 | 120
|  | DFA Quote |  |  |  | 0 | 32 |  | 0 | 0 | 32
8 | WINS Documentation | Billing - Batch & Reinstatements |  | Sasanka Sekhar Ghosh | COBOL Developer | 24 | 24 |  | 40 | 32 | 120 | 120
9 | WINS Documentation | Dwelling Fire DFA, Data Dictonary |  | Sumit Mukhopadhyay | COBOL Lead | 16 | 0 |  | 40 | 32 | 128 | 128
|  | DFA Quote |  |  |  | 0 | 20 |  | 0 | 0
|  | MCA Field Mapping Dwxp Dmbp Files Policy |  |  |  | 0 | 5 |  | 0 | 0
|  | DFA Screen Field Mapping |  |  |  | 0 | 10 |  | 0 | 0
|  | Cancellation N Reinstatement |  |  |  | 0 | 5 |  | 0 | 0
10 | Python Raters Rewrite PAP | UAT Testing Support PAP |  | Kartikey Pant | Python Developer | 24 | 16 |  | 10 | 10 | 60 | 60
11 | WINS Documentation | Documentation & ERD Review |  | Piuesh Jain | PM | 4 | 7.5 |  | 8 | 6 | 25.5 | 100.5
| Devops Setup & Support | DevOps Setup & Configuration |  |  |  | 11 | 12 |  | 12 | 10 | 75
| PBI & Sharepoint Support | Power BI Reports |  |  |  | 0 | 14 |  | 0 | 0
| RPA Report Support | Reports Review & Support |  |  |  | 1 | 3 |  | 0 | 0
12 | WINS Documentation | Workflows |  | Teena Walia | BA | 4 | 8 |  | 20 | 20 | 55 | 55
| RPA Report Support | RPA support |  |  |  | 0 | 3 |  | 0 | 0
13 | Quincy General Professional Services | PAP Python Rewite Prod Dev |  | Vinod Ramamurthy | SME | 3 | 2 |  | 5 | 3 | 13 | 126
|  | WINS Documentation |  |  |  | 5 | 0 |  | 23 | 14 | 42
|  | Adhoc requests from Shashi |  |  |  | 0 | 16 |  | 1 | 1 | 18
|  | QOL 2.0 MCA |  |  |  | 2 | 3 |  | 3 | 2 | 13
|  | Client Meetings |  |  |  | 1 | 4 |  | 2 | 1 | 8
|  | SIRs |  |  |  | 5 | 14 |  | 7 | 6 | 32
14 | Devops Setup & Support | Devops Setup & Configuration |  | Bhawesh Pant | Devops & Data Engineer | 2 | 2 |  | 5 | 5 | 22 | 22
| WINS Documentation | ERD and sharepoint |  |  |  | 2 | 2 |  | 2 | 2
15 | Quincy General Professional Services | Data Dictonary and Snapshot queries |  | Ravindra Singh | SME | 12 | 0 |  | 20 | 16 | 48 | 48
16 | WINS Documentation | Documentation and review |  | Ritam Chakraborty | COBOL Developer | 24 | 32 |  | 40 | 32 | 128 | 128
17 | WINS Documentation | Documentation and review |  | Sandip Kuilya | COBOL Developer | 24 | 0 |  | 40 | 32 | 96 | 120
|  | DFA Quote |  |  |  | 0 | 24 |  | 0 | 0 | 24
18 | PBI & Sharepoint Support | Power BI Reports |  | Vikas Gusain | Power BI developer | 0 | 2 |  | 0 | 0 | 2 | 2
Total
[6 empty] | 276 | 443 | 0 | 518 | 376 |  | 1627.5
Total
[9 empty] | W1 | 276
[9 empty] | W2 | 443